## Project_Data
Project ID | Project Name | Task Name | Owner | Start Date | End Date | Status | % Complete | Days Remaining | Project Health
P001 | Website Revamp | Design UI | Ravi | 2026-03-01 | 2026-03-10 | In Progress | 60 | -10 | Delayed
P002 | Website Revamp | Develop Backend | Anita | 2026-03-05 | 2026-03-15 | Not Started | 0 | -5 | Delayed
P003 | Mobile App | Login Module | Kiran | 2026-03-01 | 2026-03-08 | Completed | 100 | -12 | Completed
P004 | Mobile App | Payment Integration | Sneha | 2026-03-07 | 2026-03-20 | In Progress | 50 | 0 | On Track
P005 | Data Migration | Data Cleaning | Arjun | 2026-03-02 | 2026-03-12 | Delayed | 40 | -8 | Delayed
P006 | E-Commerce Platform Enhancement | Design UI | Raju | 2026-03-04 | 2026-03-06 | Not Started | 0 | -14 | Delayed
p007 | Security Compliance Implementation | Develop Frontend | Kavitha | 2026-04-02 | 2026-04-08 | In Progress | 30 | 19 | On Track
P008 | Security Compliance Implementation | Login Module | Prasad | 2025-04-05 | 2026-09-07 | In Progress | 10 | 171 | On Track
Formulas:
Days Remaining = [End Date]-TODAY()
Project Health = IF(H2=100,"Completed",IF(AND([End Date]<TODAY(),H2<100),"Delayed","On Track"))

## Resource_Data
Resource Name | Project Name | Task Assigned | Hours Allocated | Hours Used | Utilization %
Ravi | Website Revamp | Design UI | 40 | 25 | 62.5%
Anita | Website Revamp | Backend | 50 | 10 | 20%
Kiran | Mobile App | Login Module | 30 | 30 | 100%
Sneha | Mobile App | Payment | 45 | 20 | 44.44%
Arjun | Data Migration | Cleaning | 35 | 20 | 57.14%
Kavitha | Security Compliance Implementation | Develop Frontend | 70 | 30 | 42.86%
Prasad | Security Compliance Implementation | Login Module | 50 | 25 | 50%

## Risk_Tracker
Risk ID | Project Name | Risk Description | Severity | Status | Mitigation
R001 | Website Revamp | UI delay | High | Open | Add extra designer
R002 | Mobile App | Payment failure | High | Open | Test APIs
R003 | Data Migration | Data loss | Medium | Closed | Backup data

## Dashboard
PMO Dashboard
Total Projects | Completed Tasks | In Progress
8 | 1 | 4
Total Tasks | 8
Completed Tasks | 1
In Progress Tasks | 4
Delayed Tasks | 4
On Track Tasks | 3